K E S T R I D G E   A I

INTERNAL DOCUMENT · DELIVERY RULES

Version 1.1 · August 2026 · Kestridge AI Inc., Illinois, USA

Automation - Delivery Rules

The General Rules fully apply. Below are the operational rules, tool stack and procedures specific to automation projects.

1. Tool stack (standard)

| Purpose | Tool | When |
| --- | --- | --- |
| Low-code flows | n8n (self-hosted, privacy-friendly) | Default choice |
| Low-code (client stack) | Make / Power Automate / Zapier | If the client already uses it |
| Custom logic | Python | When API/low-code isn't enough |
| RPA (interface) | Playwright (or UiPath) | Only where there's no API |
| Secrets | Vault (1Password/Bitwarden) | Never kept in code/flows |
| Monitoring | Platform logs + alerts | Every run is tracked |

The platform account is opened in the client's name - nothing stays dependent on us.

2. What we ask from the client

A process owner - the specific person(s) who run the process today.

Test accounts - in every system to be integrated (we never work through real users' accounts).

A test environment - sandbox/test instance; where none exists, only agreed safe data.

A place to run - where the flow will live: the client's VM (standard spec: General Rules) or a platform account.

3. Build rules (mandatory in every flow)

Every automation must have these 5 things - no exceptions:

1.  Idempotency - if the same operation runs again, the result isn't duplicated (e.g. the same email isn't sent twice, the same payment isn't made twice).

2.  Retry + backoff - on a transient error, retry with exponential delay; if it ultimately fails, a dead-letter (it lands somewhere, never lost).

3.  Kill switch - the client can stop the process themselves at any moment; its location is in the runbook.

4.  Logging - every operation: when, what was done, the result. Traceable backwards.

5.  Owner - each flow has one responsible person.

Also:

API-first: use the API if one exists; RPA only where there is none (it breaks when the interface changes).

Rate limit / quota is respected - don't overload/flood the client system (a forgotten risk: an infinite loop → thousands of duplicate emails).

Financial / irreversible operations (payments, deletions, emails to customers) are first built with an approval step; fully automatic mode only after the parallel run, with written consent.

API auth: OAuth / scoped token, refresh handled properly; keys in the vault.

4. The parallel-run rule

The new automation runs alongside the old process for at least 2 weeks.

Results are compared daily; if they diverge, no cutover happens - the period is extended instead.

The old process is untouched - the way back is open.

5. Testing and deployment

The flow is built in test/staging first, and reaches production only after it's confirmed working.

Flows are versioned (export + Git); changes go through a change request.

6. Extra handover items

Workflow map: every step, every integration, every notification (trigger → action → owner).

Runbook: stop / restart / resolving typical errors.

Change guide: when one of the systems changes (new field, new version), what to check.