K E S T R I D G E   A I

INTERNAL DOCUMENT · PROJECT ROADMAP

Version 1.1 · August 2026 · Kestridge AI Inc., Illinois, USA

AI Solutions - Project Roadmap

Every step from first contact to handover. Durations are typical; exact figures are fixed in the agreement.

| # | Stage | Duration | Outcome |
| --- | --- | --- | --- |
| 0 | Inquiry & response | 1 to 2 business days | Meeting time scheduled |
| 1 | Discovery call | 30 to 45 min | Problem and goal are clear |
| 2 | Technical assessment | 3 to 5 business days | Data audit + solution option |
| 3 | Proposal & agreement | 2 to 3 business days | Signed scope + price |
| 4 | Kickoff | ~1 week | Access, environment, data ready |
| 5 | POC / pilot | 2 to 4 weeks | Working prototype, go/no-go |
| 6 | Full build | in sprints | Model + integration complete |
| 7 | Testing & validation | 1 to 2 weeks | Targets confirmed on real data |
| 8 | Go-live | 1 to 3 days | Running in production |
| 9 | Stabilization | 2 to 4 weeks | Provably stable under real load |
| 10 | Handover | 2 to 3 days | Docs, training, access revoked |

The steps

0. Inquiry & response. An inquiry arrives via the form or email. We reply within 1 to 2 business days and schedule the first meeting.

1. Discovery call. We listen: the client's problem, existing systems, the state of their data, and the expected outcome. An NDA is signed at this stage on request. This is a meeting to understand - not to sell.

2. Technical assessment. We review a data sample (quality, volume, accessibility), identify solution options and estimate the effort. If the data isn't ready for AI, we say so openly and show what needs fixing first.

3. Proposal & agreement. Scope, phases, timeline, price and acceptance criteria written as numbers (e.g. minimum accuracy, response time). The agreement is signed after approval.

4. Kickoff. Access is granted, the working environment is set up (VM / cloud project), data is transferred, the communication channel and weekly status day are agreed. Rules: see "Delivery Rules - AI Solutions".

5. POC / pilot. A working prototype is built on a limited dataset and measured against the target metrics. The result is evaluated together with the client - the continue / adjust / stop decision is made here. The approach is proven before major spend.

6. Full build. Sprint-based: the model is refined, integrated with existing systems, and an interface is built where needed. Weekly status + demo.

7. Testing & validation. In real scenarios, with the client's team involved (UAT). The acceptance criteria in the agreement are checked one by one.

8. Go-live. Production deployment + monitoring (performance, drift, errors). A rollback plan is ready in advance.

9. Stabilization. After go-live the system is watched under real load and every issue is fixed immediately. We do not hand over and leave until we are certain the system fully works - no handover before this stage is closed.

10. Handover. Documentation (architecture, configuration, runbook), a training session for the team, secure transfer of secrets, and revocation of our access. After that - the agreed support arrangement.