K E S T R I D G E   A I

INTERNAL DOCUMENT · PROJECT ROADMAP

Version 1.1 · August 2026 · Kestridge AI Inc., Illinois, USA

IT Security - Project Roadmap

Every step from first contact to handover. The iron rule: no testing starts without written authorization - not even a basic scan.

| # | Stage | Duration | Outcome |
| --- | --- | --- | --- |
| 0 | Inquiry & response | 1 to 2 business days | Meeting time scheduled |
| 1 | Discovery call | 30 to 45 min | Need is clear (audit / pentest / monitoring) |
| 2 | Scope & written authorization | 2 to 4 business days | Signed authorization + scope list |
| 3 | Proposal & agreement | 2 to 3 business days | Methodology, timeline, price signed |
| 4 | Kickoff | 2 to 3 days | Test windows, emergency contacts agreed |
| 5 | Execution (assessment) | 1 to 3 weeks | Testing completed within scope |
| 6 | Report | 3 to 5 business days | Findings by severity + remediation steps |
| 7 | Remediation support | per plan | Vulnerabilities closed |
| 8 | Retest | 2 to 5 business days | Fixes verified |
| 9 | Final report & handover | 1 to 2 days | Clean status, access revoked |

The steps

0. Inquiry & response. We reply within 1 to 2 business days and schedule the first meeting.

1. Discovery call. What is needed: a security audit, a penetration test, compliance preparation, or continuous monitoring? We get the overall picture of the environment. The NDA is usually signed right here.

2. Scope & written authorization. An exact list of what will be tested (IPs, domains, applications). Written authorization from the client's management is obtained. Nothing outside the scope is touched.

3. Proposal & agreement. Methodology, test types, timeline, price, report format. Tests that could cause a service outage enter the scope only with separate, explicit consent.

4. Kickoff. Test windows (usually outside business hours), 24/7 emergency phone contacts on both sides, and a stop procedure are agreed. Rules: see "Delivery Rules - IT Security".

5. Execution. Testing proceeds within the agreed scope and windows. A critical vulnerability is reported directly within 24 hours - we do not wait for the report.

6. Report. Findings ranked Critical / High / Medium / Low, each with: description, evidence, business risk, and a concrete remediation step. A non-technical executive summary on top. Delivered only over an encrypted channel.

7. Remediation support. The client fixes, or we fix - per the agreement. Either way, we keep answering questions throughout.

8. Retest. Closed vulnerabilities are re-verified. One retest is included at no extra charge.

9. Final report & handover. Clean status is documented, all of our access is revoked and the revocation is confirmed in the handover document. We do not close the engagement until we are certain the vulnerabilities are actually closed.

Addendum for the continuous monitoring service

If monitoring is ordered, stages 5 to 9 become: connecting log sources → 2 to 4 weeks of tuning (clearing false alarms) → escalation matrix sign-off → switch to the agreed monitoring hours → monthly reports.