A I V A N T A

INTERNAL DOCUMENT · PROJECT ROADMAP

Version 1.0 · July 2026 · AIVanta Inc., Illinois, USA

Automation — Project Roadmap

Every step from first contact to handover. The defining rule: the old process is never switched off until the new automation is proven.

| # | Stage | Duration | Outcome |
| --- | --- | --- | --- |
| 0 | Inquiry & response | 1–2 business days | Meeting time scheduled |
| 1 | Discovery call | 30–45 min | Which processes, what gain |
| 2 | Process mapping | 3–7 business days | As-is process approved in writing |
| 3 | Proposal & agreement | 2–3 business days | To-be design + price signed |
| 4 | Kickoff | ~1 week | Test accounts, environment ready |
| 5 | Build | in sprints | Workflows running in test |
| 6 | Parallel run | min. 2 weeks | Results match the old process |
| 7 | Cutover | 1–2 days | Process runs automatically |
| 8 | Stabilization | 2–4 weeks | Stable under real load |
| 9 | Handover | 2–3 days | Runbook, training, access revoked |

The steps

0. Inquiry & response. We reply within 1–2 business days and schedule the first meeting.

1. Discovery call. We listen for where time is being lost and where errors appear. The 1–3 processes with the highest payoff are selected.

2. Process mapping. We document the process step by step together with the people who run it today (screen recordings welcome). The as-is process is approved by the client in writing — automation is only built on top of a correctly understood process.

3. Proposal & agreement. The to-be (automated) process design, behavior for exceptions, scope, timeline and price. Acceptance criteria: what share of the process runs automatically, and what happens on error.

4. Kickoff. Test accounts are obtained for every system to be integrated, the test environment is set up, the communication channel is agreed. Rules: see "Delivery Rules — Automation".

5. Build. Workflows are built: via API where one exists, RPA only where there is none. Error handling + notifications at every step. Weekly status + a working demo.

6. Parallel run. The new automation runs side by side with the old process for at least 2 weeks; results are compared daily. If they diverge, the cause is found and fixed and the period is extended. The old process is untouched during this stage.

7. Cutover. Once results match, the old process is retired on an agreed day. The path back to the old process stays open.

8. Stabilization. Monitoring under real load, immediate fixes, tuning where needed. We do not hand over and leave until the process provably works.

9. Handover. Runbook (how to stop, restart, and resolve typical errors), team training, access revocation. After that — the agreed support arrangement.